## Budget Cost Control
Project Budget - Cost Controlling & Forecasting
Estimates | [13 empty] | Total | Avg
Working days |  | 19 | 20 | 20 | 15 | 22 | 21 | 20 | [5 empty] | 137 | 19.5714
Forecast: Vacation days |  |  | 2 | 1 | [9 empty] | 3 | 1.5
Forecast: Working hours (h/day) | 7.5 | 142.5 | 135 | 142.5 | 112.5 | 165 | 157.5 | 150 | 0 | 0 | 0 | 0 | 0 | 1005 | 83.75
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | [7 empty] | Hourly rate
Dev Backend | Luke Frost | [12 empty] | 4 |  | 350 | bar: Nov to Feb
Dev Backend | Ryan Blaze | [12 empty] | 4 |  | 350 | bar: Nov to Feb
Dev Frontend | Adam Stone | [12 empty] | 4 |  | 300 | bar: Nov to Feb
Dev Frontend | Eric Storm | Nov: 0.5; Dec: 0.5; Jan: 0.5; Feb: 0.5 | [5 empty] | 2 |  | 300
QA | Mark Rivers | [12 empty] | 4 |  | 200 | bar: Nov to Feb
PM | Tom Night | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.2 | [5 empty] | 0.8 |  | 280
| Sum FTE | 4.7 | 4.7 | 4.7 | 4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.8
Forecast: Total hours per month |  | 669.75 | 634.5 | 669.75 | 528.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502.75 | 208.5625
| Forecast: Costs | 200355 | 189810 | 200355 | 158175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748695 | 62391.25
| Invoiced costs | [12 empty] | 0 | #DIV/0! | below budget
| Deviation | -200355 | -189810 | -200355 | -158175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -748695 | -62391.25 | -100%
| Cumulated Invoiced Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulated Invoiced Costs % | [7 empty] | 0% | 0% | 0% | 0% | 0% | bar: Nov to May
| Forecast: Cumulated costs % | 26.76% | 52.11% | 78.87% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Forecast: Cumulated costs | 200355 | 390165 | 590520 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695
| Deviation | 200355 | 390165 | 590520 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695 | 748695
[13 empty] | Approved budget | 748695
[13 empty] | Remaining budget | 748695
[13 empty] | Remaining Forecast | 748695
[13 empty] | Spent budget | 0
Spent Hours
Dev Backend | Luke Frost
Dev Backend | Ryan Blaze
Dev Frontend | Adam Stone
Dev Frontend | Eric Storm
QA | Mark Rivers
PM | Tom Night
Sum(h) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Difference
Dev Backend | Luke Frost
Dev Backend | Ryan Blaze
Dev Frontend | Adam Stone
Dev Frontend | Eric Storm
QA | Mark Rivers
PM | Tom Night
Sum(h) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Budget Forcasting
Project Budget - Cost Controlling & Forecasting
Estimates | [13 empty] | Total | Avg
Working days |  | 19 | 20 | 20 | 20 | 22 | 21 | 20 | [5 empty] | 142 | 20.2857
Forecast: Vacation days |  |  | 2 | 1 | 0 | 13 | [7 empty] | 16 | 4
Forecast: Working hours (h/day) | 7.5 | 142.5 | 135 | 142.5 | 150 | 67.5 | 157.5 | 150 | 0 | 0 | 0 | 0 | 0 | 945 | 78.75
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | [7 empty] | Hourly rate
Dev Backend | Luke Frost | [12 empty] | 5 |  | 350 | bar: Nov to Mar
Dev Backend | Ryan Blaze | [12 empty] | 5 |  | 350 | bar: Nov to Mar
Dev Frontend | Adam Stone | [12 empty] | 5 |  | 300 | bar: Nov to Mar
Dev Frontend | Eric Storm | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 2.5 |  | 300
QA | Mark Rivers | [12 empty] | 5 |  | 200 | bar: Nov to Mar
PM | Tom Night | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [7 empty] | 1 |  | 280
0
0
0
| Sum FTE | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5
Forecast: Total hours per month |  | 669.75 | 634.5 | 669.75 | 705 | 317.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996.25 | 249.6875
| Forecast: Costs | 200355 | 189810 | 200355 | 210900 | 94905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896325 | 74693.75
| Invoiced costs | Nov: 202000; Dec: 160000 | [5 empty] | 362000 | 181000 | below budget
| Deviation | 1645 | -29810 | -200355 | -210900 | -94905 | 0 | [6 empty] | -534325 | -89054.1667 | -71.37%
| Cumulated Invoiced Costs | Nov: 202000; Dec: 362000
| Cumulated Invoiced Costs % | 26.98% | 48.35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Forecast: Cumulated costs % | 26.76% | 52.11% | 78.87% | 107% | 119.7% | 119.7% | 0% | 0% | 0% | 0% | 0% | 0%
| Forecast: Cumulated costs | 200355 | 390165 | 590520 | 801420 | 896325 | 896325
| Deviation | Nov: -1645; Dec: 28165; Jan: 590520
[13 empty] | Approved (Orginal estimate) budget | 748695
[13 empty] | Forcast: Budget | 896325
[13 empty] | Deviation | -147630
[13 empty] | Spent budget | 362000
[13 empty] | Remaining orignal budget | 386695
[13 empty] | Remaining Forecast | 305805