## Chart
Project Status

## Model_all
Month Name | Sprint No | Sprint No | Sprint | Start | Stop | Working days | Devs (FTE) | Original Scope | Backlog Scope | Delivered Scope [Total] | P15 Trendline | P50 Trendline | Pessimistic Original Plan | Optimal Original Plan | Velo Pessimistic per sprint/dev | Velocity Optimal per Sprint/dev | Pessimistic Plan per Sprint | Optimal Plan per Sprint | Trend per Sprint (p15) | Trend per Sprint (p50) | Delivered Scope per Sprint | P15 | P50 | Velo Pes - per day/dev | Velo Op - per day/dev | Div Scope
Nov | 1 | 03.11-16.11 | Sprint 1 | 2025-11-03 | 2025-11-16 | 9 | 3.5 | 900 | 900 | 121 |  |  | 121 | 121 | 31.5 | 40.5 | 110.25 | 141.75 | 110.6 | 127 | 121 | 110.6 | 127 | 3.5 | 4.5 | 98
Nov | 2 | 17.11-30.11 | Sprint 2 | 2025-11-17 | 2025-11-30 | 10 | 3.5 | 900 | 900 | 261 |  |  | 243.5 | 278.5 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127 | 140 |  |  | 35h x 1 dev/sprint | 45h x 1 dev/sprint
Dec | 3 | 01.12-14.12 | Sprint 3 | 2025-12-01 | 2025-12-14 | 10 | 3.5 | 900 | 920 | 393 |  |  | 366 | 436 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127 | 132
Dec | 4 | 15.12-28.12 | Sprint 4 | 2025-12-15 | 2025-12-28 | 7 | 3.5 | 900 | 940 | 488 |  |  | 451.75 | 546.25 | 24.5 | 31.5 | 85.75 | 110.25 | 110.6 | 127 | 95
Dec | 5 | 29.12-11.01 | Sprint 5 | 2025-12-29 | 2026-01-11 | 7 | 3.5 | 900 | 998 | 615 | 615 | 615 | 537.5 | 656.5 | 24.5 | 31.5 | 85.75 | 110.25 | 110.6 | 127 | 127
Jan | 6 | 12.01-25.01 | Sprint 6 | 2026-01-12 | 2026-01-25 | 10 | 3.5 | 900 | 998 |  | 725.6 | 742 | 660 | 814 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127
Jan | 7 | 26.01-08.02 | Sprint 7 | 2026-01-26 | 2026-02-08 | 10 | 3.5 | 900 | 998 |  | 836.2 | 869 | 782.5 | 971.5 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127
Feb | 8 | 09.02-22.02 | Sprint 8 | 2026-02-09 | 2026-02-22 | 10 | 3.5 | 900 | 998 |  | 946.8 | 996 | 905 | 1129 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127
Feb | 9 | 23.02-08.03 | Sprint 9 | 2026-02-23 | 2026-03-08 | 10 | 3.5 | 900 | 998 |  | 1057.4 | 1123 | 1027.5 | 1286.5 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127
Mar | 10 | 08.03-21.03 | Sprint 10 | 2026-03-09 | 2026-03-22 | 10 | 3.5 | 900 | 998 |  | 1168 | 1250 | 1150 | 1444 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127
Mar | 11 | 21.03-03.04 | Sprint 11 | 2026-03-23 | 2026-04-05 | 10 | 3.5 | 900 | 998 |  | 1278.6 | 1377 | 1272.5 | 1601.5 | 35 | 45 | 122.5 | 157.5 | 110.6 | 127

## Model_BE
Month Name | Sprint No | Sprint No | Sprint | Start | Stop | Working days | Devs (FTE) | Original Scope | Backlog Scope | Delivered Scope [Total] | P15 Trendline | P50 Trendline | Pessimistic Original Plan | Optimal Original Plan | Velo Pessimistic per sprint/dev | Velocity Optimal per Sprint/dev | Pessimistic Plan per Sprint | Optimal Plan per Sprint | Trend per Sprint (p15) | Trend per Sprint (p50) | Delivered Scope per Sprint | P15 | P50 | Velo Pes - per day/dev | Velo Op - per day/dev | Div Scope | Additional days to cover
Nov | 1 | 03.11-16.11 | Sprint 1 | 2025-11-03 | 2025-11-16 | 9 | 2 | 500 | 500 | 66 |  |  | 63 | 81 | 31.5 | 40.5 | 63 | 81 | 57.6 | 68 | 66 | 57.6 | 68 | 3.5 | 4.5 | 78 | 13.5417
Nov | 2 | 17.11-30.11 | Sprint 2 | 2025-11-17 | 2025-11-30 | 10 | 2 | 500 | 500 | 146 |  |  | 133 | 171 | 35 | 45 | 70 | 90 | 57.6 | 68 | 80 |  |  | 35h x 1 dev/sprint | 45h x 1 dev/sprint
Dec | 3 | 01.12-14.12 | Sprint 3 | 2025-12-01 | 2025-12-14 | 10 | 2 | 500 | 500 | 214 |  |  | 203 | 261 | 35 | 45 | 70 | 90 | 57.6 | 68 | 68
Dec | 4 | 15.12-28.12 | Sprint 4 | 2025-12-15 | 2025-12-28 | 7 | 2 | 500 | 520 | 259 |  |  | 252 | 324 | 24.5 | 31.5 | 49 | 63 | 57.6 | 68 | 45
Dec | 5 | 29.12-11.01 | Sprint 5 | 2025-12-29 | 2026-01-11 | 7 | 2 | 500 | 578 | 331 | 331 | 331 | 301 | 387 | 24.5 | 31.5 | 49 | 63 | 57.6 | 68 | 72
Jan | 6 | 12.01-25.01 | Sprint 6 | 2026-01-12 | 2026-01-25 | 10 | 2 | 500 | 578 |  | 388.6 | 399 | 371 | 477 | 35 | 45 | 70 | 90 | 57.6 | 68
Jan | 7 | 26.01-08.02 | Sprint 7 | 2026-01-26 | 2026-02-08 | 10 | 2 | 500 | 578 |  | 446.2 | 467 | 441 | 567 | 35 | 45 | 70 | 90 | 57.6 | 68
Feb | 8 | 09.02-22.02 | Sprint 8 | 2026-02-09 | 2026-02-22 | 10 | 2 | 500 | 578 |  | 503.8 | 535 | 511 | 657 | 35 | 45 | 70 | 90 | 57.6 | 68
Feb | 9 | 23.02-08.03 | Sprint 9 | 2026-02-23 | 2026-03-08 | 10 | 2 | 500 | 578 |  | 561.4 | 603 | 581 | 747 | 35 | 45 | 70 | 90 | 57.6 | 68
Mar | 10 | 08.03-21.03 | Sprint 10 | 2026-03-09 | 2026-03-22 | 10 | 2 | 500 | 578 |  | 619 | 671 | 651 | 837 | 35 | 45 | 70 | 90 | 57.6 | 68
Mar | 11 | 21.03-03.04 | Sprint 11 | 2026-03-23 | 2026-04-05 | 10 | 2 | 500 | 578 |  | 676.6 | 739 | 721 | 927 | 35 | 45 | 70 | 90 | 57.6 | 68

## Model_FE
Month Name | Sprint No | Sprint No | Sprint | Start | Stop | Working days | Devs (FTE) | Original Scope | Backlog Scope | Delivered Scope [Total] | P15 Trendline | P50 Trendline | Pessimistic Original Plan | Optimal Original Plan | Velo Pessimistic per sprint/dev | Velocity Optimal per Sprint/dev | Pessimistic Plan per Sprint | Optimal Plan per Sprint | Trend per Sprint (p15) | Trend per Sprint (p50) | Delivered Scope per Sprint | P15 | P50 | Velo Pes - per day/dev | Velo Op - per day/dev | Div Scope | Additional days to cover
Nov | 1 | 03.11-16.11 | Sprint 1 | 2025-11-03 | 2025-11-16 | 9 | 1.5 | 400 | 400 | 55 |  |  | 47.25 | 60.75 | 31.5 | 40.5 | 47.25 | 60.75 | 53 | 55 | 55 | 53 | 55 | 3.5 | 4.5 | 20 | 3.7736
Nov | 2 | 17.11-30.11 | Sprint 2 | 2025-11-17 | 2025-11-30 | 10 | 1.5 | 400 | 400 | 115 |  |  | 99.75 | 128.25 | 35 | 45 | 52.5 | 67.5 | 53 | 55 | 60 |  |  | 35h x 1 dev/sprint | 45h x 1 dev/sprint
Dec | 3 | 01.12-14.12 | Sprint 3 | 2025-12-01 | 2025-12-14 | 10 | 1.5 | 400 | 420 | 179 |  |  | 152.25 | 195.75 | 35 | 45 | 52.5 | 67.5 | 53 | 55 | 64
Dec | 4 | 15.12-28.12 | Sprint 4 | 2025-12-15 | 2025-12-28 | 7 | 1.5 | 400 | 420 | 229 |  |  | 189 | 243 | 24.5 | 31.5 | 36.75 | 47.25 | 53 | 55 | 50
Dec | 5 | 29.12-11.01 | Sprint 5 | 2025-12-29 | 2026-01-11 | 7 | 1.5 | 400 | 420 | 284 | 284 | 284 | 225.75 | 290.25 | 24.5 | 31.5 | 36.75 | 47.25 | 53 | 55 | 55
Jan | 6 | 12.01-25.01 | Sprint 6 | 2026-01-12 | 2026-01-25 | 10 | 1.5 | 400 | 420 |  | 337 | 339 | 278.25 | 357.75 | 35 | 45 | 52.5 | 67.5 | 53 | 55
Jan | 7 | 26.01-08.02 | Sprint 7 | 2026-01-26 | 2026-02-08 | 10 | 1.5 | 400 | 420 |  | 390 | 394 | 330.75 | 425.25 | 35 | 45 | 52.5 | 67.5 | 53 | 55
Feb | 8 | 09.02-22.02 | Sprint 8 | 2026-02-09 | 2026-02-22 | 10 | 1.5 | 400 | 420 |  | 443 | 449 | 383.25 | 492.75 | 35 | 45 | 52.5 | 67.5 | 53 | 55
Feb | 9 | 23.02-08.03 | Sprint 9 | 2026-02-23 | 2026-03-08 | 10 | 1.5 | 400 | 420 |  | 496 | 504 | 435.75 | 560.25 | 35 | 45 | 52.5 | 67.5 | 53 | 55
Mar | 10 | 08.03-21.03 | Sprint 10 | 2026-03-09 | 2026-03-22 | 10 | 1.5 | 400 | 420 |  | 549 | 559 | 488.25 | 627.75 | 35 | 45 | 52.5 | 67.5 | 53 | 55
Mar | 11 | 21.03-03.04 | Sprint 11 | 2026-03-23 | 2026-04-05 | 10 | 1.5 | 400 | 420 |  | 602 | 614 | 540.75 | 695.25 | 35 | 45 | 52.5 | 67.5 | 53 | 55